## Slide 1
COUNTY OF SANTA CLARA SOLAR PV PROJECT
DESIGNED AND CONSTRUCTED BY SUNPOWER
COMMUNITY MEETING
Pearl Avenue Branch Library- 4270 Pearl Ave, San Jose, CA 95136
July 12, 2016, 5PM – 8PM

## Slide 2
PROJECT OVERVIEW:
Project location: West of Southbound Highway 87, between Capital Expressway and Branham Lane, in San Jose.
System type: Ground mounted fixed tilt
System size: 2.1 Megawatts (enough to power 215 homes)
Project saving: Saving of $7.1 Million in electricity costs over a 25 years period.
* Very low impact use of land post construction (limited to no noise, minimal lighting, and non-visible from the residential side)

## Slide 3: Project’s Environmental Attributes
System Clean Renewable Electricity = 3,421,713 KWH / Year
CO2 Emissions Avoidance = 2,405 Metric Tons / Year (EPA Calculator)
What does this mean?

## Slide 4: Project Site Access and Challenges

## Slide 5: Initially Contemplated Access Points
Access Point – From Guadalupe Fwy (Not Granted by CalTrans)
Access Point – From Capitol Expy (Temporary Access)
Access Point – From Seabury Dr.
(In Progress of Pursuing Access)

## Slide 6: Initial Project Site Access Points by Priority
Guadalupe/87 Freeway -Caltrans
a. Geotechnical Engineering Survey Access –Approved
b. Construction Phase Access –Not Approved
c. Maintenance & Operations Access –Not Approved
Capitol Expressway
a. Existing Improvised Access with limitations
b. No Permanent Access from Capital Expressway (No Driveway)
c. Access for ~80% of Project’s Construction Material & Equipment
Sound-wall at Seabury Drive
a. Access for Remaining 20% of Construction Activities (~8 Weeks)
b. Access for Post-Construction (O&M, Emergency Response Vehicles, PG&E)
c. Lockable Sound Attenuating Gates (Maintained Lock)

## Slide 7
Project photos, as of July 8, 2016

## Slide 8
Seabury Dr. Construction Access:
  Minimal Number of Delivery Trucks
  2-3 tractor trailers for electrical switch gear (one time)
  3 cement truck for electrical equipment pad and fence post (one time)
  Truck for site services (1 truck/week for 8 weeks)
  Light trucks (construction crew and tools, 8 weeks)
  Work hours: 7AM – 5PM, M – F
Seabury Dr. After Construction Access:
  Solar PV System Service Vehicle 2-4 times per year.
  Emergency Response Vehicles
  PG&E
  County of Santa Clara Inspections (Property Owner)
With Sound-Wall Gate at Seabury Dr.

## Slide 9
SITE ACCESS PREPARATION:
  Sound-wall Panel Removal Duration: 2 days.
  Gate Fabrication Duration: 2-3 weeks*.
  Gate Installation Duration: 3-5 days.
  *A temporary fence with acoustical blankets for sound attenuation will be temporarily installed while the permanent gate is manufactured.
Gate perspective
Sound Attenuating Gate
Professionally Designed & Engineered.
Professional Acoustical Review of Proposed Sound Attenuating Gate.
Gate Renderings Created for Visualization Purposes; Actual Gate Finish May Vary.

## Slide 10
POST CONSTRUCTION ACTIVITIES & TRAFFIC IMPACTS:
Limited/no noise, minimal night lighting, non-visible from the westerly residential side.
Solar PV system maintenance: 2 to 4 visits annually for solar PV system servicing/maintenance and vegetation management. Typical visit will consist of 1-2 technicians in light pickup truck or van.
*Minimal
NON-VISIBLE FROM THE RESIDENTIAL SIDE
TRAFFIC IMPACTS
MINIMAL

## Slide 11: Sound-Wall Modification Alternative
Crane Large Equipment Over Sound-Wall at Seabury Drive
Pump Concrete over Sound-Wall at Seabury Drive

## Slide 12
Please submit your questions/comments at this time.

## Slide 13: Contact Information
County of Santa Clara
Ca Le (Project Coordinator)
Phone: (408) 993-4637
Email: Ca.Le@faf.sccgov.org
Lin Ortega (Project Manager)
Phone: (408) 993-4643
Email: Lin.Ortega@faf.sccgov.org
SunPower
Charlie Tate (Construction Manager)
Phone: (415) 373-7758
Email: Charlie.Tate@sunpower.com
Cion Trujillo (Project Manager)
Phone: (510) 260-8409
Email: Cion.Trujillo@sunpower.com